- MUNICIPAL TURNAROUND TEMPLATE – UBUNTU  MUNICIPALITY

| No. | Priority Turn Around Focal Area |  |  |  | January 2010 (Current Situation/ Baseline) |  |  |  | Target for December 2010 (Changed Situation) |  | Municipal Action |  |  | Unblocking Action Needed from other Spheres and Agencies (e.g. intervention or technical support) |  | Human Resource allocated |  | Budget |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Allocated |  | Projected |
| 1. | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Access to water management and maintenance |  |  |  | VICTORIA WEST: - Provision of water contract – AM Conroy that is providing about 50% of water |  |  |  | April 2010 |  | Source a legal opinion – Contract proposed evaluation |  |  | Legal opinion from DWA & COGSHTA & DBSA |  | Municipal Manager & Technical Manager |  |  |  |  |
|  |  |  |  |  | - Finalization of Water Provision (20 households outstanding) |  |  |  | April 2010 |  | Project Completion by own work force |  |  |  |  | Technical Manager |  |  |  |  |
|  |  |  |  |  | - Replacement of old asbestos reticulation pipes (ageing infrastructure @ Richmond & Loxton) |  |  |  | Funding Sourcing |  | Business Plan |  |  | DWA – MIG to look at alternative funding |  | Technical Manager |  |  |  |  |
|  |  |  |  |  | - Overconsumption and waste of water (1000 without metres @ Richmond & Loxton) |  |  |  | Review present policy; and Facilitation funds; and Facilitate a procurement process; and Contractor on site by December 2010 |  | Report back process with all stakeholders; Review policy; & Facilitate procurement process |  |  | DWA, DBSA Technical Support – Legal Process |  | Technical Manager CFO |  |  |  |  |
|  |  |  |  |  | - Shortage of water bore holes |  |  |  | Bore a sufficient number of bore holes for the municipal water demand |  | Request the bore hole drilling machine |  |  | DWA– Bore hole development team |  | Technical manager |  |  |  |  |
|  |  |  |  |  | RICHMOND: See point 3, 4, 5 & 6 LOXTON: See point 2,3,4,5 & 6 |  |  |  |  |  |  |  |  |  |  | Technical Manager |  |  |  |  |
| 1.2 | Access to sanitation management & maintenance |  |  |  | VICTORIA WEST: Bulk infrastructure on 70 sites not yet in place |  |  |  | To install a sewerage network on the outstanding 70 sites |  | Install the network |  |  | COGTA integrated planning COGHSTA to release funding for 270 houses |  | Mayor, Municipal Manager & Technical Manager |  |  |  |  |
|  |  |  |  |  | LOXTON: All have full water borne systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | RICHMOND: Informal sites about 70 buckets |  |  |  | Town establishment process finalised |  | Monitor process |  |  | COGTA & COGHSTA to finalise this process as a matter of urgency with Dept of Human Settlement |  |  |  |  |  |  |
| 1.3 | Access to electrical management & maintenance |  |  |  |  |  |  |  |  |  |  |  |  | Long term infrastructure planning and funding |  |  |  |  |  |  |
|  |  |  |  |  | LOXTON: 36 households must still be supplied with electricity |  |  |  |  |  | Liaise with Eskom |  |  | DME & SALGA to facilitate the process |  |  |  |  |  |  |
| 1.4 | Refuse Removal, Victoria West, Richmond & Loxton |  |  |  | Upgrading of Land fill sites |  |  |  | Complete the feasibility study |  | EIA feasibility study Victoria West landfill Sites, planning & managing, cleaning and upgrade of Landfill sites licensing of landfill sites |  |  | DWA & Environmental Affairs |  | Technical Manager |  |  |  |  |
| 1.5 | Access and maintenance of municipal roads |  |  |  | Gravel roads in town in need of repair |  |  |  |  |  | COGHSTA & Dept of Roads & District municipality to discuss to graders by municipalities |  |  |  |  |  |  |  |  |  |
| 1.6 | Formalisation of informal settlements |  |  |  | VICTORIA WEST: Bulk infrastructure on 70 sites not yet in place RICHMOND: Informal sites about 70 buckets |  |  |  | To install a sewerage network on the outstanding 70 sites Town establishment process finalised |  | Install the network Monitor process |  |  | COGTA integrated planning COGHSTA to release funding for 270 houses COGTA & COGHSTA to finalise this process as a matter of urgency with Dept of Human Settlement |  | Mayor, Municipal Manager & Technical Manager |  |  |  |  |
| 2. |  | Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 |  | Functionality of Ward Committees |  |  |  | All ward committees functional Further training necessary |  |  |  | To facilitate ward committee members that are temporary employed in the road maintenance project Facilitate the training process of ward committee members |  |  |  | SALGA & COGHSTA COGHSTA to facilitate the debate surrounding the remuneration of ward committee members | Mayor & Corporate Manager |  | 70 000 |  |  |  |
| 2.2 |  | Broader public participation policies and plans |  |  |  | Interaction with community not satisfactory |  | Programme must be adopted by Council of bi-monthly meetings with stakeholders |  | Develop program for Council meets the people bi-monthly |  |  |  | COGHSTA to facilitate the process of getting sector departments involved in local government issues | Speaker, Municipal Manager & Ward Councillors |  | 30 000 |  |  |  |
| 2.3 |  | Broader public participation |  |  |  | Only public meetings & notices |  | Issue a municipal news letter on a bi-monthly basis |  | To publish a news letter |  |  |  |  | Office of the Mayor & MM |  | 20 000 |  |  |  |
| 2.4 |  | Complaints management systems |  |  |  | We have a complaints register (system is lacking) |  | Monthly |  | To enhance the functionality of the register (Richmond to receive special attention) |  |  |  |  | Manager & Heads of Dept. |  | 10 000 |  |  |  |
| 2.5 |  | Front Desk Interface |  |  |  | Operational but can be enhanced The offices at Victoria West, Richmond & Loxton not accessible for the disabled |  | To make the two offices accessible for the disabled |  | To discuss & plan the proposed alterations to the 3 offices To facilitate the process in making the 2 offices accessible |  |  |  |  | Municipal Manager & Technical Manager |  | 50 000 |  |  |  |
| 2.6 |  | Appointment of CDW’s vs. number of wards |  |  |  | 4 wards, 7 CDW’s and one vacancy (Richmond) |  |  |  |  |  |  |  | COGHSTA to facilitate the debate of the transferring of funds and the authority to appoint CDW’s by municipalities and the development of applicable guidelines in this respect |  |  | n/a |  |  |  |
| 3. |  |  |  | Governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 |  |  |  | Political Management and Oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 |  |  |  | Stability of Councils |  | Needs better implementation and clarity needs improvement Not fully operational |  | March 2010 March 2010 March 2010 March 2010 |  | Council Item Council Item Council Item Council Item |  |  |  |  |  |  | 10 000 |  |  |  |
| 3.1.2 |  |  |  | Delegation of functions between political and administration |  | Serviced by the District Council No proper oversight |  |  |  | - Budget for Committee - Advertise for services & appointment – headhunting - Training on legislation - Mayor attending (ELMPD) |  |  |  |  | Mayor & manager SALGA |  | 80 000 |  |  |  |
| 3.1.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 |  |  |  | Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 |  |  |  | Recruitment, Selection and Suspension of employees |  | No suspensions Two arbitration cases pending Process of recruitment of s57 appointments as well as other appointments underway Recruitment policy in place (no review) |  | To appoint the Technical Manager & the CFO |  | To conclude the process of advertising, short listing, interviews & appointments |  |  |  |  |  |  | 80 000 |  |  |  |
| 3.2.2 |  |  |  | Vacancies (Top 4- MM, CFO, Planner, Engineer) |  | Vacancies- Technical Manager & CFO |  | Appointment of both |  | To follow due process as above |  |  |  |  |  |  | 20 000 |  |  |  |
| 3.2.3 |  |  |  | Vacancies in other levels |  | Functional organogram 57 vacancies |  | To fill 60% of those posts by 30 June 2010 |  | To complete the recruitment & appointment process by 30 June 2010 |  |  |  |  | Corporate Manager |  | 20 000 |  |  |  |
| 3.2.4 |  |  |  | Top 4 appointed with signed Performance Agreements |  | Two appointed both signed Performance agreements |  |  |  |  |  |  |  |  |  |  | 100 000 |  |  |  |
| 3.2.5 |  |  |  | IDP adopted by Council |  | Yes |  |  |  |  |  |  |  |  |  |  | 150 000 |  |  |  |
| 3.2.6 |  |  |  | SDBIP adopted by Council |  | Yes approved by the Mayor |  |  |  |  |  |  |  |  |  |  | 20 000 |  |  |  |
| 3.2.7 |  |  |  | Organisational Performance Management System |  | Only for s57 employees Policy in place |  |  |  |  |  |  |  |  |  |  | Part of 3.2.4 |  |  |  |
| 3.2.8 |  |  |  | S 46 report for 2008/09 adopted by Council |  |  |  |  |  |  |  |  |  |  |  |  | n/a |  |  |  |
| 3.2.9 |  |  |  | Mid-year assessment report for 2009/10 adopted by Council |  | YES |  |  |  |  |  |  |  |  |  |  | n/a |  |  |  |
| 3.2.10 |  |  |  | Performance Audit Committee (PAC) appointed |  | NO |  |  |  |  |  |  |  |  |  |  | 50 000 |  |  |  |
| 3.2.11 |  |  |  | PAC report presented to Council |  | NO |  |  |  |  |  |  |  |  |  |  | n/a |  |  |  |
| 3.2.12 |  |  |  | Skills Audit conducted for all employees |  | YES |  |  |  | A new audit will be done |  |  |  |  |  |  | 100 000 |  |  |  |
| 3.2.13 |  |  |  | Skills development for employees |  | Skills development plan in place |  |  |  |  |  |  |  |  |  |  | 50 000 |  |  |  |
| 3.3 |  |  |  | Labour Relations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 |  |  |  | Functionality of Local Labour Relations |  | YES (gender equity not yet reached) |  |  |  |  |  |  |  |  |  |  | 30 000 |  |  |  |
| 3.3.2 |  |  |  | Functionality of LLF |  | Functions effectively |  |  |  |  |  |  |  |  |  |  | Part of 3.3.1 |  |  |  |
| 4. |  |  | Financial Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 |  |  | Revenue enhancement |  |  |  |  |  |  |  |  |  |  |  |  |  | 300 000 |  |  |  |
| 4.2 |  |  | Debt management |  |  |  |  |  |  |  |  |  |  |  |  |  | 150 000 |  |  |  |
| 4.3 |  |  | Cash flow management |  |  |  |  |  |  |  |  |  |  |  |  |  | 50 000 |  |  |  |
| 4.4 |  |  | Repairs and maintenance provision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.5 |  |  | Capital expenditure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.6 |  |  | Clean Audit |  |  |  |  |  |  |  |  |  |  |  |  |  | 800 000 |  |  |  |
| 4.7 |  |  | Submission of Annual Financial Statements |  |  |  |  |  |  |  |  |  |  |  |  |  | 50 000 |  |  |  |
| 4.8 |  |  | MIG expenditure |  |  | Under spending | Total spend by 31 March 2010 |  |  |  |  | Submit latest expenditure report Enhance expenditure Train personnel in MIGMIS for reporting |  |  |  |  | 50 000 |  |  |  |
| 4.9 |  |  | Asset management |  |  |  |  |  |  |  |  |  |  |  |  |  | 600 000 |  |  |  |
| 4.10 |  |  | Credibility and transparency of Supply Chain Management |  |  |  |  |  |  |  |  |  |  |  |  |  | 50 000 |  |  |  |
| 5. |  |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 |  |  | LED Strategy adopted by Council |  |  | NO |  |  |  |  |  |  | DBSA to assist with process |  |  |  | 500 000 |  |  |  |
| 5.2 |  |  | LED Plan aligned to the PGDS and adopted by Council |  |  | NO |  |  |  |  |  |  |  |  |  |  | 100 000 |  |  |  |
| 5.3 |  |  | LED manager appointed |  |  | NO | To be appointed by 31 March 2010 |  |  |  |  | Appoint the official |  |  | Corporate Services |  | 30 000 |  |  |  |